## Sheet1
Log Number | Team Member | Date | Hours | Minutes | Description |  | Hours | Minutes
1 | Aiden Patel, Andrew McFerrin, John Newman, Kai Achen, Landon Pyko | 2025-01-29 | 1 | 0 | discuss project idea and begin requirements stack | Aiden Patel | 33 | 22
2 | Aiden Patel, Andrew McFerrin, John Newman, Kai Achen, Landon Pyko | 2025-02-02 | 1 | 0 | finalize initial requirements stack | Andrew McFerrin | 31 | 12
3 | John Newman | 2025-02-06 | 0 | 30 | wrote two requirements artifacts | John Newman | 13 | 18
4 | Landon Pyko | 2025-02-05 | 0 | 15 | wrote one artifact. forgot to write this down yesterday | Kai Achen | 11 | 25
5 | Landon Pyko | 2025-02-06 | 0 | 20 | Looked into Hugging Face and CNN. Made the GitHub repository and shared it with group | Landon Pyko | 19 | 5
6 | John Newman | 2025-02-06 | 0 | 19 | wrote 2 requirements artifacts
7 | Aiden Patel | 2025-02-07 | 0 | 20 | organized documentation on GitHub. Started initial architecture document and then remembered we have a writer on the team that'll be better at that
8 | Aiden Patel | 2025-02-07 | 0 | 30 | did a little bit of research on models and put in some starter code to get an idea of what's going on | Total Time | 108 | 22
9 | Kai Achen | 2025-02-10 | 1 | 0 | completed DubBot training programs to learn more about how alt-text works and what makes effective and successful alt-text.
10 | Andrew McFerrin | 2025-02-10 | 0 | 30 | Looked into a couple image datasets and tried to generally understand whats even going on
11 | Landon Pyko | 2025-02-12 | 0 | 45 | Did some research and think that ResNet50 will be good for image classification. Imported some starter code for it. Also made a .gitignore to ignore the venv/ directory for if people want to use a virtual environment for dependencies
12 | Landon Pyko | 2025-02-12 | 0 | 30 | Spent a lot of time downloading dependencies and setting up venv. Created an instructions folder for everyone else for setting up the environment for it. Modified starter code to take in a image that I put in an image file. Properly classifies the image in output!
13 | Aiden Patel | 2025-02-12 | 0 | 40 | put in some starter code using DETR model that can generate multiple tags per image
14 | Kai Achen | 2025-02-12 | 0 | 35 | created compile_to_csv function that compiles images, tags, and flags into a csv file format for later use
15 | Aiden Patel, Andrew McFerrin | 2025-02-12 | 0 | 15 | discussed implementation of models
16 | Aiden Patel | 2025-02-12 | 1 | 0 | got some starter code in for entity recognition for text context and then burned a bunch of time messing with venv stuff because I don't have enough storage to download the GPU stuff for pytorch on my main drive
17 | Aiden Patel | 2025-02-13 | 1 | 30 | create tag_synthesizer that takes in tags and creates a caption and also created create_caption that takes in a photo and text to combine them and make a caption. Put some examples in and there's one in place on create_caption to test it (I know it's an illogical photo and text combo but that's the point)
18 | Landon Pyko | 2025-02-13 | 0 | 15 | Started on Sprint 2 Requirements Artifacts
19 | Aiden Patel | 2025-02-13 | 0 | 45 | set up environment on my desktop. made a requirements.txt to automatically install every package we need. proibably will need to update it. now trying to get the model to run on my gpu, not working so far but will report back
20 | Aiden Patel, Landon Pyko | 2025-02-13 | 0 | 5 | discuss running model on Nvidia cards
21 | Aiden Patel, Andrew McFerrin | 2025-02-13 | 0 | 12 | talk about models and realize we need another model for extracting text found on an image
22 | Landon Pyko | 2025-02-13 | 1 | 15 | Finally got it to work on my gpu.... frankly it took like twice as long as i said but i don't want to put that time in the log
23 | Aiden Patel, Landon Pyko | 2025-02-13 | 0 | 30 | talk through some code and about models being used
24 | Aiden Patel | 2025-02-14 | 0 | 45 | Rename files to be more descriptive and add caption model that helps create final output better
25 | Andrew McFerrin | 2025-02-14 | 1 | 15 | Familiarized myself with project, finished up rest of artifacts for sprint 2.
26 | Landon Pyko | 2025-02-14 | 1 | 0 | Fixed up tag generation by merging words together that started with ##. Weird thing that was happening but this fixed it. Also, did some other random stuff and made the sentence generator output grammatically correct sentences, even if it means they lose some of their meaning
27 | Aiden Patel | 2025-02-14 | 0 | 40 | Created a test script to batch test image and text combos
28 | John Newman | 2025-02-14 | 1 | 40 | Researched databases for training. Found one, attempted to trim dead links. Timeframe is on the scale of days. Not really feasible. Database is still usable, just program around using dead links
29 | John Newman | 2025-02-14 | 1 | 37 | Researched how to train models, spent time prompt engineering, banged my head against a wall, discussed and thought about how model will work and train
30 | Kai Achen | 2025-02-15 | 0 | 20 | tinkered with torch cuda sentence generator prompt using some verbiage from the section508.gov site on what makes appropriate alt-text
31 | Kai Achen | 2025-02-15 | 0 | 20 | created flow chart artifact for what type of alt-text should be generated based on image attributes and website context
32 | Landon Pyko | 2025-02-15 | 0 | 30 | Did some comments
33 | Aiden Patel | 2025-02-16 | 1 | 10 | Added URL image functionality and created 'main' facing method for captioner to connect with scraper in the future
34 | Aiden Patel | 2025-02-16 | 0 | 20 | create worklog
35 | Aiden Patel | 2025-02-16 | 0 | 5 | cleaned up sprint 2 artifacts and submitted it as well as the requirements stack
36 | Aiden Patel | 2025-02-21 | 0 | 5 | fork sprint 1 repo for second sprint and invited the team for collaboration
37 | Aiden Patel | 2025-02-21 | 1 | 10 | Created web scraper and connected it to the captioner in the main_captioner.py file. Ran the test on the lied center site so the output can be seen at lied_center.csv
38 | Aiden Patel | 2025-02-21 | 0 | 23 | create quick script to convert csv output to pdf to show caption next to image
39 | Aiden Patel | 2025-02-21 | 0 | 8 | add pdf creator to test script
40 | Kai Achen | 2025-02-24 | 0 | 20 | learn Aiden's new changes and write some basic information in the README on how to use the project in its current state
41 | Kai Achen | 2025-02-24 | 0 | 30 | fix some import statements and attempted to make web scraper also access images in "revolution slider" (lied specific wordpress plugin) but not working correctly yet
42 | Kai Achen | 2025-02-24 | 0 | 5 | added timer to main_captioner.py
43 | Andrew McFerrin | 2025-02-24 | 0 | 15 | reviewed sprint requirements and understood the scraper code
44 | Landon Pyko | 2025-02-24 | 1 | 0 | tried tinkering with some model generation inputs but didn't make much progress, will look at it again tomorrow
45 | Aiden Patel | 2025-02-24 | 0 | 20 | pushed potentially broken code because I wanted to have it saved in case of a crash. Created test function to test multiple sites so I'm going to run that now to get timings
46 | Aiden Patel | 2025-02-24 | 0 | 20 | thought something was broken with the code so i was crashing out but realized i forgot the 'u' at the end of 'edu' in a url and that's why it was breaking
47 | Aiden Patel | 2025-02-24 | 0 | 30 | added bypass for images that have failures processing or process nothing
48 | Aiden Patel | 2025-02-24 | 0 | 5 | added another thing to handle poor response code from loading an image
49 | Aiden Patel | 2025-02-24 | 0 | 10 | handle poor response code from loading image in PDF creator
50 | Aiden Patel | 2025-02-24 | 0 | 3 | more try except blocks added to catch errors in image loading
51 | Andrew McFerrin | 2025-02-24 | 2 | 0 | Worked on new branch "front_end" to reorganize structure of project to facilitate flask. Created basic flask website with initial necessary elements. Reran main_captioner to ensure it still works with restructured project
52 | Aiden Patel | 2025-02-25 | 0 | 10 | added another dead link check and reviewed test results
53 | Aiden Patel | 2025-02-25 | 0 | 36 | Ran tests and put in some starter code for multiprocessing that is currently blocked from running
54 | Aiden Patel | 2025-02-25 | 1 | 15 | update multiprocessing to be functional without ruining single process option. Ran test on lied center and found 210 second decrease in run time when using 4 processes over 1
55 | Aiden Patel | 2025-02-25 | 0 | 10 | update worklog
56 | Aiden Patel | 2025-02-25 | 1 | 30 | organize files and change code so that dependencies still work and input and output files are handled correctly
57 | Kai Achen | 2025-02-25 | 1 | 0 | restructuring to prepare for Flask implementation and added some functionality for users to mark types of images
58 | Aiden Patel | 2025-02-25 | 1 | 0 | rebase front_end branch to updated file structure. Talk with Kai about file structure so moved new file structure over to main branch. Need to rebase front_end to updated file structure
59 | Aiden Patel | 2025-02-25 | 0 | 10 | pull up flags and front_end_rebase branches to newest version of main with the updated file structure
60 | Aiden Patel | 2025-02-25 | 0 | 15 | fixed path issue and created multiprocess test function to get optimal number of processes
61 | Aiden Patel | 2025-02-26 | 0 | 20 | fix multiprocess test to run on lied center with 1-16 processes
62 | Aiden Patel | 2025-02-26 | 0 | 5 | ran pool tests, everything failed. Pushing results anyway to show how many got through before crashing
63 | Landon Pyko | 2025-02-27 | 1 | 15 | spent forever on dependencies. the flask is acting weird, not sure if it is on just my device or not. started outputting what the errors are. someone else can try to fix that. it might be a me problem but i have no idea
64 | Landon Pyko | 2025-02-27 | 0 | 10 | I got it to not crash on my laptop so that's good
65 | John Newman | 2025-02-28 | 1 | 27 | Spent time researching ways to detect and load desired images
66 | Landon Pyko | 2025-03-01 | 1 | 30 | Flask runs scaper and model when url is input. Once data is finished being process it renders a success page. Someone else could do putting the images with the captions on the flask website for output. for now they just print in the terminal
67 | Aiden Patel | 2025-03-01 | 1 | 30 | generalized the pythonn executable used in index.py so it shouldn't have to be changed between systems. Added output page that loads all images and their alt text after processing is done
68 | Kai Achen | 2025-03-03 | 0 | 20 | updated requirements stack and assigned a few tasks
69 | Aiden Patel | 2025-03-04 | 0 | 10 | update worklog
70 | Andrew McFerrin | 2025-03-04 | 1 | 55 | Reviewed previous video, created script document, wrote/planned out part of script, and made mascot image
71 | Andrew McFerrin | 2025-03-04 | 3 | 10 | Resolved issues with setting up my environment, created intro to video
72 | Andrew McFerrin | 2025-03-06 | 0 | 30 | Wrote/planned out script for website demo on video
73 | Landon Pyko | 2025-03-06 | 0 | 30 | Wrote some stuff for the script and looked more into how to refine our alt text. doing the cosine similarity stuff could be more difficult than we think
74 | Kai Achen | 2025-03-06 | 0 | 30 | Added some words to the script about refined front end and authorization
75 | Andrew McFerrin | 2025-03-06 | 4 | 0 | continued work on the video
76 | Landon Pyko | 2025-03-07 | 0 | 20 | did some stuff
77 | Andrew McFerrin | 2025-03-07 | 3 | 30 | more editing
78 | Kai Achen | 2025-03-07 | 2 | 0 | added to script and created documentation on data types used in each function of the project
79 | John Newman | 2025-03-07 | 1 | 45 | added to script
80 | Kai Achen | 2025-03-08 | 2 | 0 | finalized script and helped find and create some assets for video
81 | Andrew McFerrin | 2025-03-08 | 3 | 0 | more video wow
82 | Andrew McFerrin | 2025-03-08 | 0 | 15 | lil bit o video
83 | Andrew McFerrin | 2025-03-08 | 3 | 0 | finished video(?)
84 | Kai Achen | 2025-03-09 | 0 | 15 | helped make a few more assets for video
85 | Andrew McFerrin | 2025-03-09 | 0 | 15 | Made final adjustments
86 | John Newman | 2025-03-10 | 1 | 0 | made new branch for training the model. made dummy code for when we actually have datasets.
87 | Aiden Patel | 2025-03-11 | 0 | 5 | create pull request for flags branch and merged it over with main
88 | Landon Pyko | 2025-03-12 | 1 | 0 | Made a new branch, reinstalled dependencies on my machine and changed a few lines but now it's not finding my csv??
89 | Landon Pyko | 2025-03-13 | 0 | 35 | It runs but now the output is dog water
90 | Aiden Patel | 2025-03-13 | 0 | 30 | update requirements stack and create artifacts
91 | Aiden Patel | 2025-03-13 | 0 | 10 | update worklog
92 | Aiden Patel | 2025-03-13 | 1 | 0 | Separated scrape and process functions and added function to remove images from CSV. Hitting issues with testing that is causing it to fail to write to CSV
93 | John Newman | 2025-03-14 | 0 | 29 | More work on training file, changed prompt a bit. No real results
94 | Aiden Patel | 2025-03-25 | 0 | 5 | add pycache to gitignore
95 | Aiden Patel | 2025-03-25 | 0 | 30 | finished separating backend functions to allow for exclusions
96 | Aiden Patel | 2025-03-25 | 0 | 45 | created database and started to integrate it into captioning process
97 | John Newman | 2025-03-25 | 0 | 20 | Added support to store training data from captioning process
98 | Andrew McFerrin | 2025-03-25 | 3 | 20 | Created front end for manual image tagging
99 | Andrew McFerrin | 2025-03-26 | 0 | 50 | tried to figure out how to send image link csv to front end
100 | Aiden Patel | 2025-03-26 | 0 | 5 | figure out how to amend commit to remove leaked API key
101 | Landon Pyko | 2025-03-26 | 3 | 0 | Changed model from FLAN-T5 to gemini, seems very promising with about the same runtime. Accidentally leaked the API key (lol) so we tried to fix that. Merged and the old key.txt came back up but it's an old key so it can't be used. Aiden is going to just manually delete the old key.txt file. They can see it in our history but it's dead now anyways so it doesn't matter
102 | Aiden Patel | 2025-03-27 | 1 | 10 | Hashing into database and fetching them later is now working. Need to make it where timestamps update on each retrieval and DB purges when it hits a certain size but I'll get to it later
103 | Aiden Patel | 2025-03-27 | 0 | 23 | Changed where timestamp updates for each access and DB will purge the oldest timestamp when more than 500 entries are present. Also added flag in create_caption that can be changed when forcing the model to not check the DB and compute instead
104 | Aiden Patel | 2025-03-27 | 1 | 10 | Updated index.py on main branch and pulled up image_exclusions and cache_computations branches with new changes. Moved functionality in image_exclusions branch into new main.py function but will need to be split later. Ran site tests on cache branch to update database. Database hashing is probably ready to merge into main soon but will likely cause a few merge conflicts on other branches
105 | Landon Pyko | 2025-03-27 | 2 | 0 | Entirely removed the text processing step from the pipeline, and have gemini working with the output. I also tried seeing how gemini's image captioning would be (as opposed to blip's) and it's lowkey better. Anyways, I just made a different captioning function that calls gemini instead of blip so everything is still in there and we can evaluate output later
106 | Landon Pyko | 2025-03-28 | 0 | 20 | Looking into chrome extensions
107 | Aiden Patel | 2025-03-28 | 1 | 0 | Talked to Landon about Gemini and merged into main. Pulled up other branches to have new changes. Ran tests on cache branch to begin updating database with new Gemini responses
108 | Aiden Patel | 2025-03-28 | 4 | 0 | Connected selection function with front end to allow for user tagging
109 | Kai Achen | 2025-03-29 | 0 | 10 | update requirements stack
110 | Aiden Patel | 2025-03-29 | 0 | 30 | cleaned up image_exclusions branch and merged into main
111 | Aiden Patel | 2025-03-29 | 0 | 20 | update cache branch with main and then merged it into main
112 | Andrew McFerrin | 2025-03-30 | 0 | 30 | Created sprint 5 artifacts document
113 | Andrew McFerrin | 2025-03-30 | 0 | 30 | Watched a few videos on how to set up tailwind in a project and basic use
114 | John Newman | 2025-03-30 | 2 | 0 | Updated files for training. create_caption.py: changed gemini generate to call with training args gemini.py: added arguments for training, added code to collect data if training train_flan.py: Changed code to just be for cleaning up datasets and providing good data to them. Added a tkinter image and entry for data collection.
115 | John Newman | 2025-03-30 | 0 | 11 | Added some things to sprint 5 artifacts.
116 | Aiden Patel | 2025-03-30 | 0 | 17 | Finished requirements stack and artifacts for sprint 5 and submitted
117 | Aiden Patel | 2025-03-30 | 0 | 10 | update worklog
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200