## Requirements Stack
REQUIREMENTS STACK:
Requirement ID | Description | Story Points | Priority | Sprint Number | Story Point Totals | Notes | Total story points estimated:
1 | Choose model (Hugging Face) | 3 | 1 | 1 | 33 |  | 135
2 | Find image dataset to train model on | 3 | 1 | 1
3 | Find text dataset to train model on | 3 | 1 | 1
4 | Write Training Algorithm | 13 | 1 | 1
5 | Train model on dataset | 8 | 1 | 1
6 | Design output data format | 3 | 1 | 1
7 | Image->alt-text intermediate step | 5 | 1 | 2 | 37
8 | Create text webscraper | 8 | 2 | 2
9 | Create image webscraper | 8 | 2 | 2
10 | Interpret text scraped data | 5 | 2 | 2
11 | Interpret image scraped data | 5 | 2 | 2
12 | Create function interface for scraper | 3 | 2 | 2
13 | Test model on scraped data | 3 | 3 | 2
14 | Choose front end framework (Flask) | 2 | 3 | 3 | 31
15 | Design front end UI | 8 | 3 | 3
16 | Create front end | 8 | 3 | 3
17 | Back end integration with front end | 13 | 3 | 3
18 | Break up functions to allow exclusions from processing | 8 | 4 | 4 | 34
19 | Front end support to exclude images from scraped site | 5 | 5 | 4
20 | Store past computations in database | 8 | 4 | 4
21 | Create demo site to show precomputed results | 13 | 5 | 4
22 | OAuth Integration to store past results | 8 | 6 | 5
23 | Create API for embedded use | 21 | 4 | 5
24 | API Integration and Testing | 21 | 4 | 6
25 | Existing alt-text predictive verification | 21 | 5 | 6 |  | Subject to dropping if we need to push any of the previous sprints further than expected